## Summary
Defects summary for project RNG Certification for multiple games for UK From 2024-05-07 to 2024-05-09
Project: RNG Certification for multiple games for UK (baonl.2400001)
CLIENT / LICENSEE: Base Online NV
Description | High | Medium | Low | Clarifications Needed | Total
Open | 0 | 5 | 0 | 0 | 5
To be Retested | 0 | 0 | 0 | 0 | 0
Failed retest | 0 | 0 | 0 | 0 | 0
Fixed | 0 | 0 | 0 | 0 | 0
Invalid, closed | 0 | 0 | 0 | 0 | 0
Total Outstanding | 0 | 5 | 0 | 0 | 5
Please view 'Details' worksheet for detailed information of the above defects

## Details
| Open | Priority 3: High,must be fixed |  |  | Priority 1: Low,optional to fix
| Failed retest | Priority 2: Medium,must be fixed or work around must be provided |  |  | Priority 0: Clarification needed
Defects details for project RNG Certification for multiple games for UK (baonl.2400001)
ID | Category | Sub-Category | Priority | Description | Comments | Client Comments | Status
2403411 | Source Code Evaluation | Source Code | 2 (Medium) | Subject: Clarification regarding Algorithm Description: In the provided source code, there are separate isaac files for Dice and Plinko. However, in the provided screenshot, only one isaac file is visible. If multiple isaac files are being used for each game, we suggest using a centralized isaac file that can be invoked for all games. Please provide us with the updated one. Steps to Reproduce: N/A | Defect created by suryanarayanan on 2024-05-07 |  | Open
2403412 | Source Code Evaluation | Source Code | 2 (Medium) | Subject: Clarification regarding Scaling Description: 1] In the file "DiceController.php" and @line #242, we see that the only mod operation is being used to scale the random number. The current implementation will induce skewness/ bias in the calls, depending upon the mod value. A proper scaling method that would not create such bias needs to be used. Here, we suggest extracting a long from the first 53 bits (or higher) from the random number and then dividing the number resulting by 2^53 -1(or higher i.e. 2^ bits - 1) to get the uniformly scaled double value [0,1] which then it can be multiplied with the bound to attain the value between the ranges. In case you want to use [0,1), then divide by 2^53 (or higher 2^bits) instead. 2] Also, we noticed that in the same code, you are invoking Isaac() at line #241 to generate outcomes. But we couldn't find the actual implementation of that method in the provided code. Kindly provide the same. However, for the game "Plinko" (i.e. PlinkoController.php), we couldn't find this method invoked or used. Instead, it appears that outcomes are generated based on the server seed, client seed, and nonce. Please clarify this. Steps to Reproduce: N/A | Defect created by suryanarayanan on 2024-05-07 |  | Open
2403413 | Source Code Evaluation | Source Code | 2 (Medium) | Subject: Clarification regarding server seed and client frequency/creation Description: We see the variables serverseed and clientseed being used in the provided files. Could you please let us know how the both seed are created and also let us know the frequency of serverSeed and clientSeed creation in the current implementation which is further passed to get the random number. Steps to Reproduce: N/A | Defect created by suryanarayanan on 2024-05-07 |  | Open
2403421 | Source Code Evaluation | Source Code | 2 (Medium) | Subject: Clarification regarding Game Snippets and Range/Intervals Description: Please let us know the possible ranges/intervals (for eg, for slots, this would be referring to reel lengths and for cards) for all the game types in scope. Also, in the provided game snippets, we could see the snippets only for Dice and Plinko. But, in the provided scope we see Roulette, Instant(crash) and Keno game types are also included. Kindly provide us the corresponding game snippets for the same. Steps to Reproduce: N/A | Defect created by suryanarayanan on 2024-05-08 |  | Open
2403422 | Source Code Evaluation | Source Code | 2 (Medium) | Subject: Clarification regarding OS version and software being used in production Description: Please confirm the operating system being used in the production and its details i.e. if you are using Linux then please provide the kernel version. This is just for our internal tests run. Also, please let us know the PHP version used here. Since it is lib based RNG, we need to baseline the same. Steps to Reproduce: N/A | Defect created by suryanarayanan on 2024-05-08 |  | Open

## Images
Defect Id | Images
2403411
2403412
2403413
2403421
2403422